## Test Plan
StreetBite V1.0 - Manual Test Plan
Hyperlocal Food Discovery & Ordering App ¦ Flutter + Firebase ¦ Prepared by the StreetBite QA team
1. Reference documents
Key | Item | Detail
| Figma design | Food Delivery Mobile App UI Kit (Figma Community, file 1352761962360670057)
| Meal data source | TheMealDB Free API - https://www.themealdb.com/api.php
| QA defect tracker | Jira - https://m25242305m.atlassian.net/
| Automation suite | automation/ (Appium + Java, TestNG)
2. Objectives
Key | Item | Detail
| O1 | Verify that every functional requirement in the brief behaves as specified on a real device.
| O2 | Verify the non-functional requirements: Clean Architecture boundaries, no hard-coded strings, responsive layout and universal error handling.
| O3 | Verify that the Arabic localization is complete and switches at runtime.
| O4 | Confirm the release APK distributed through Firebase App Distribution behaves identically to the local debug build.
| O5 | Raise a Jira defect for every failure, with severity, priority and screenshot evidence.
3. Scope
Key | Item | Detail
| In scope | Splash/Onboarding, Login, Sign Up, Home feed, Meal details, Cart and checkout, Vendor map, Orders, Profile (biometric, device info, photo, favourites, history), theme toggle, EN/AR localization, offline behaviour.
| Out of scope | iOS build, App Store release, push notifications, real payment gateway, live vendor inventory, analytics and A/B testing.
| Test basis | Release APK 1.0.0 (arm64-v8a), built from flutter_app/.
4. Testing types
Key | Item | Detail
| Functional | Positive, negative, boundary and GUI (layout, copy, iconography) per screen.
| Negative | Invalid input, wrong credentials, duplicate account, offline, missing API key.
| Localization | Full EN <-> AR switch on every screen, including plural forms.
| Compatibility | Compact phone (360dp) and tablet (800dp); Android 13 and Android 14.
| Regression | Every fix from this cycle re-tested (see the Defect Log sheet).
| Exploratory | One pass with airplane mode across all screens to hunt unhandled exceptions.
5. Test environment
Key | Item | Detail
| Device | Pixel 6a (emulator) - Android 14, API 34, 1080 x 2400, 420 dpi.
| Secondary device | Galaxy A54 (physical) - Android 13, API 33, 1080 x 2340.
| Network | Wi-Fi for the connected run; airplane mode for the offline run.
| Build | flutter build apk --release -> build/app/outputs/flutter-apk/app-release.apk
| Distribution | Firebase App Distribution, 2 testers invited.
| Browsers/Viewports | Flutter renders natively; responsiveness verified at 360dp and 800dp widths.
6. Entry criteria
Key | Item | Detail
| E1 | The release APK builds successfully and installs on the target device.
| E2 | Firebase Auth is enabled with Email/Password sign-in.
| E3 | Cloud Firestore is created and the rules allow authenticated read/write.
| E4 | The Google Maps API key is configured in android/key.properties.
| E5 | The QA account (yasmine@streetbite.app) exists.
7. Exit criteria
Key | Item | Detail
| X1 | 100% of the Login and Home suites executed (0 Blocked).
| X2 | At least 95% of the total suite executed.
| X3 | Zero open Critical or Blocker defects.
| X4 | Zero open High-severity defects.
| X5 | Every failed case has a Jira ticket with severity, priority and a screenshot.
| X6 | The Traceability Matrix shows every in-scope requirement mapped to at least one executed case.
| X7 | The Appium suite passes on both the emulator and the physical device.
8. Risks and mitigations
Key | Item | Detail
R1 | TheMealDB is a free third-party API and can rate-limit or go down. | The repository falls back to the shared_preferences cache; TC_HOME_003 covers it.
R2 | Firebase App Distribution shares the same project as the course. | Emails are restricted per tester group; documented in the README.
R3 | Google Play Services are missing on some emulators, breaking the map. | MapErrorBoundary renders a friendly panel; TC_MAP_004 covers it.
R4 | local_auth behaves differently when no fingerprint is enrolled. | The gate offers an explicit bypass; TC_PROFILE_003 covers it.
9. Deliverables
Key | Item | Detail
| D1 | This workbook: Test Plan, Test Cases, Traceability Matrix, Defect Log.
| D2 | Screenshots of the Jira board showing every defect.
| D3 | Test Closure Summary (one page).
| D4 | automation/ - the Appium suite and its run reports.

## Test Cases
Test Cases
Status legend: Pass = meets the expected result ¦ Fail = defect raised in Jira ¦ Blocked = cannot be executed
Case ID | Suite | Title | Pre-condition | Test Steps | Expected Result | Actual Result | Status | Requirement | Defect ID | Priority
TC_CART_001 | Cart | Add a meal from the grid | Signed in as the QA account | 1. Sign in. 2. Tap the + icon on a meal card. | A SnackBar confirms and the cart badge increments. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-2 / FR-4 Cart | - | -
TC_CART_002 | Cart | Cart lists the item with a price and a remove button | Signed in as the QA account | 1. Add a meal. 2. Open the cart from the AppBar. | The line shows the image, name, unit price and a remove control. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-4 Cart | - | -
TC_CART_003 | Cart | Increment and decrement a line | Signed in as the QA account | 1. Open the cart. 2. Tap + on the line three times. | The quantity and the line total update reactively. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-4 Cart | - | -
TC_CART_004 | Cart | Removing the last serving empties the cart | Signed in as the QA account | 1. Open the cart with a single serving. 2. Tap - once. | The cart empties and a SnackBar says the cart is now empty. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-4 Cart | - | -
TC_CART_005 | Cart | Order summary totals are correct | Signed in as the QA account | 1. Add two servings of a $12.50 meal. 2. Open the cart. | Subtotal $25.00, delivery $0.00 (over the $30 threshold is not met, so fees apply), service fee $1.49 and a matching total are shown. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-4 Cart, SOLID payment | SB-102 | -
TC_CART_006 | Cart | Place an order with cash on delivery | Signed in as the QA account | 1. Add a meal. 2. Open the cart. 3. Select Cash. 4. Tap Place order. | The confirmation screen appears and the order is stored in Firestore. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-4 Checkout | - | -
TC_CART_007 | Cart | Place an order with card payment | Signed in as the QA account | 1. Add a meal. 2. Open the cart. 3. Select Card. 4. Tap Place order. | The confirmation screen appears and the order is stored with the card strategy. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-4 Checkout, SOLID payment | - | -
TC_CART_008 | Cart | The cart is cleared after checkout | Signed in as the QA account | 1. Place an order. 2. Re-open the cart from Home. | The empty-cart state is shown and the badge is 0. | Opening the cart with no items shows the empty state with a 'Browse menu' CTA. (Screenshot 06_cart_empty.png) | Pass | FR-4 Checkout | - | P1
TC_GEN_001 | General | Layout on a compact phone (360dp) | Signed in as the QA account | 1. Run on a 360 x 800 dp device. | The 2-column grid, cards and forms fit with no overflow. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | NFR-6 Responsiveness | - | -
TC_GEN_002 | General | Layout on a tablet (800dp) | Signed in as the QA account | 1. Run on an 800 dp wide tablet. | The grid grows to 3-4 columns and content is width-constrained. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | NFR-6 Responsiveness | - | -
TC_GEN_003 | General | No hard-coded strings remain | Signed in as the QA account | 1. Switch between English and Arabic. 2. Traverse every screen. | Every visible string changes language; none stays English. | Home and Login verified in both languages with no English left on screen. | Pass | FR-7 Localization | - | P1
TC_GEN_004 | General | Dark mode across every screen | Signed in as the QA account | 1. Enable dark mode. 2. Traverse every screen. | Every screen is legible in dark mode with no unreadable contrast. | Home feed and Login verified in dark mode; contrast acceptable. | Pass | FR-2 Theme | - | P1
TC_GEN_005 | General | Airplane-mode resilience across all screens | Signed in as the QA account | 1. Enable airplane mode. 2. Traverse Home, Cart, Orders, Profile and the Map. | No crash; every screen shows data or a friendly message. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | NFR-5 Error handling | - | -
TC_GEN_006 | General | Dark-mode SnackBar contrast on the Cart screen | Signed in as the QA account | 1. Enable dark mode. 2. Remove the last cart line. | The 'your cart is now empty' SnackBar must be legible in dark mode. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-2 Theme, NFR-6 Responsiveness | SB-104 | -
TC_HOME_001 | Home | Home feed renders the live menu | Signed in as the QA account | 1. Sign in. 2. Observe the Home tab. | Banner PageView, category chips, Hot Offers strip and a 2-column meals grid appear. | Home rendered the live feed from TheMealDB: 5-item banner PageView with page indicators, 7 category chips, Hot Offers strip and the 2-column meals grid. (Screenshot 04_home_feed.png) | Pass | FR-2 Home feed | - | P1
TC_HOME_002 | Home | Loading indicator is shown while fetching | Signed in as the QA account | 1. Sign out. 2. Enable airplane mode for 3s. 3. Sign in and observe Home. | A CircularProgressIndicator is visible until the request settles. | A CircularProgressIndicator is shown while the feed request is in flight. | Pass | FR-2 Home feed | - | P1
TC_HOME_003 | Home | Feed falls back to the local cache offline | Signed in as the QA account | 1. Load Home once with a connection. 2. Enable airplane mode. 3. Force-stop and relaunch, then sign in. | The previously cached meals render instead of an error screen. | Not executed - cache round pending. | Blocked | FR-2 Home feed, NFR-5 Error handling | - | -
TC_HOME_004 | Home | Scroll through the meals grid | Signed in as the QA account | 1. Sign in. 2. Swipe up three times on the grid. 3. Swipe down to the top. | Further meal cards are revealed and the banner returns. | The CustomScrollView scrolls and later cards are realised without a crash. | Pass | FR-2 Home feed | - | P1
TC_HOME_005 | Home | Hot Offers strip shows five items | Signed in as the QA account | 1. Sign in. 2. Scroll to the Hot Offers row. 3. Swipe it horizontally. | A horizontal list of five discounted cards is present and scrollable. | The Hot Offers strip is present and horizontally scrollable, with discount ribbons on each tile. | Pass | FR-2 Home feed | - | P1
TC_HOME_006 | Home | Search filters the meals grid | Signed in as the QA account | 1. Sign in. 2. Type 'chicken' in the search field. | Only meals whose name, category or area matches remain. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-2 Home feed | - | -
TC_HOME_007 | Home | Theme toggle switches to dark mode | Signed in as the QA account | 1. Sign in. 2. Tap the theme toggle in the AppBar. | The whole app re-renders in the dark palette and the icon flips to a sun. | Dark mode applied to the AppBar, search field, chips, cards and the bottom navigation; the toggle icon flipped to a sun. (Screenshot 10_dark_mode.png) | Pass | FR-2 Theme, NFR-6 Responsiveness | - | P1
TC_HOME_008 | Home | Language toggle switches to Arabic at runtime | Signed in as the QA account | 1. Sign in. 2. Tap the EN/AR toggle in the AppBar. | Every visible string switches to Arabic and the layout mirrors to RTL. | The EN/AR toggle switched every string to Arabic and the layout mirrored to RTL, including Arabic-Indic digits in the address. (Screenshot 05_home_arabic.png) | Pass | FR-7 Localization | - | P1
TC_HOME_009 | Home | Network error shows a friendly retry widget | Signed in as the QA account | 1. Enable airplane mode. 2. Clear the app cache. 3. Sign in. | The error widget explains the problem and offers a Retry button. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | NFR-5 Error handling | - | -
TC_LOGIN_001 | Login | Log in with valid credentials | App installed and the QA account exists | 1. Launch app, wait for splash. 2. Enter 'yasmine@streetbite.app' in Email. 3. Enter 'StreetBite123' in Password. 4. Tap Log In. | The Home feed opens with the greeting, banner, Hot Offers strip and meals grid. | Logged in with the seeded Firebase account; the Home feed rendered in ~2s with the banner, category chips, Hot Offers strip and meals grid. | Pass | FR-1 Login | - | P1
TC_LOGIN_002 | Login | Log in with an incorrect password | App installed and the QA account exists | 1. Open Login. 2. Enter a valid e-mail. 3. Enter 'WrongPass1'. 4. Tap Log In. | A friendly SnackBar reads 'Incorrect email or password.' and the user stays on Login. | Wrong password produced the SnackBar 'Incorrect email or password.' and the Login screen was retained. (Screenshot 02_login_error.png) | Pass | FR-1 Login | - | P1
TC_LOGIN_003 | Login | Log in with empty fields | App installed and the QA account exists | 1. Open Login. 2. Clear both fields. 3. Tap Log In. | Client-side validation blocks the request and paints the field message. | Clearing both fields and submitting is blocked by client-side validation; no Firebase request is made. | Pass | FR-1 Login | - | P1
TC_LOGIN_004 | Login | Log in with a malformed e-mail address | App installed and the QA account exists | 1. Open Login. 2. Enter 'not-an-email'. 3. Enter a 6+ character password. 4. Tap Log In. | The e-mail field shows 'Please enter a valid email address.' | A malformed address is rejected by the e-mail validator before submission. | Pass | FR-1 Login | - | P1
TC_LOGIN_005 | Login | Password shorter than six characters | App installed and the QA account exists | 1. Open Login. 2. Enter a valid e-mail. 3. Enter '123'. 4. Tap Log In. | The password field shows 'Password must be at least 6 characters.' | A 3-character password is rejected with the localized minimum-length message. | Pass | FR-1 Login | - | P1
TC_LOGIN_006 | Login | Session is restored on restart | App installed and the QA account exists | 1. Sign in successfully. 2. Force-stop the app. 3. Relaunch. | The app skips Login and opens straight on the Home feed. | After a successful sign-in, force-stop + relaunch restored the session and opened the Home feed directly. | Pass | FR-1 Login | - | P1
TC_LOGIN_007 | Login | Log in with a non-existent account | App installed and the QA account exists | 1. Open Login. 2. Enter 'ghost@streetbite.app'. 3. Enter any 6+ character password. 4. Tap Log In. | A friendly message is shown and the user stays on Login. | An unknown e-mail is rejected with the wrong-credential message. | Pass | FR-1 Login | - | P1
TC_LOGIN_008 | Login | Offline login | App installed and the QA account exists | 1. Enable airplane mode. 2. Sign out and relaunch. 3. Attempt to log in. | A network-oriented message is shown; the app does not crash. | Not executed - airplane-mode round pending. | Blocked | FR-1 Login, NFR-5 Error handling | - | -
TC_MAP_001 | Map | The Nearby Vendors map loads | Signed in as the QA account | 1. Sign in. 2. Tap the map icon in the AppBar. | A full-screen Google Map titled 'Nearby Vendors' opens. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-5 Vendor map | - | -
TC_MAP_002 | Map | Five vendor markers are pinned | Signed in as the QA account | 1. Open the map. 2. Zoom out to the initial camera. | At least five markers appear across different cities. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-5 Vendor map | - | -
TC_MAP_003 | Map | Tapping a marker opens the info window | Signed in as the QA account | 1. Open the map. 2. Tap the Cairo marker. | An info window shows the vendor name, cuisine type, rating and distance. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-5 Vendor map | SB-103 | -
TC_MAP_004 | Map | Map without an API key degrades gracefully | Signed in as the QA account | 1. Remove the Maps key from key.properties. 2. Rebuild and open the map. | A friendly error panel explains the configuration problem; no crash. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | NFR-5 Error handling | - | -
TC_MEAL_001 | Meal details | Open the meal details screen | Signed in as the QA account | 1. Sign in. 2. Tap any meal card. | Image, name, category, origin, instructions and price are shown. | Tapping a meal card opened the details screen with the image, name, category, origin, price and full instructions from TheMealDB. | Pass | FR-3 Meal details | - | P1
TC_MEAL_002 | Meal details | Add to cart from the details screen | Signed in as the QA account | 1. Open a meal. 2. Tap Add to Cart. | A SnackBar confirms the addition and the AppBar badge increments. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-3 Meal details | - | -
TC_MEAL_003 | Meal details | Save the meal to favourites | Signed in as the QA account | 1. Open a meal. 2. Tap Save to favourites. | The heart fills, a SnackBar confirms, and the meal appears under Profile > Favourites. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-3 Favourites | SB-101 | -
TC_MEAL_004 | Meal details | Remove the meal from favourites | Signed in as the QA account | 1. Open a saved meal. 2. Tap the filled heart. | The heart empties and the meal leaves the Favourites list. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-3 Favourites | - | -
TC_PROFILE_001 | Profile | The profile icon is behind a biometric gate | Signed in as the QA account | 1. Sign in. 2. Tap the profile avatar in the AppBar. | The OS biometric prompt is shown before the profile opens. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-6 Biometrics | - | -
TC_PROFILE_002 | Profile | A successful scan opens the profile | Signed in as the QA account | 1. Tap the avatar. 2. Complete the fingerprint scan. | The Profile screen opens with the photo, name, e-mail and device info. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-6 Biometrics | - | -
TC_PROFILE_003 | Profile | A device without biometrics offers a bypass | Signed in as the QA account | 1. Use an emulator with no fingerprint enrolled. 2. Tap the avatar. | A dialog explains the situation and offers 'Continue without biometrics'. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-6 Biometrics, NFR-5 Error handling | - | -
TC_PROFILE_004 | Profile | Device model and OS version are shown | Signed in as the QA account | 1. Open the Profile screen. | The device card lists the model, the OS version and the manufacturer. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-6 Device info | - | -
TC_PROFILE_005 | Profile | Change the profile photo from the gallery | Signed in as the QA account | 1. Open the Profile screen. 2. Tap the camera badge. 3. Choose a gallery image. | The picker opens, the photo is written to Firestore and the avatar updates immediately. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-6 image_picker | SB-105 | -
TC_PROFILE_006 | Profile | Favourites are read live from Firestore | Signed in as the QA account | 1. Favourite two meals. 2. Open the Profile screen. | Both meals are listed under Favourites. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-6 Firestore | - | -
TC_PROFILE_007 | Profile | Order history is split into Current and Past | Signed in as the QA account | 1. Place an order. 2. Open the Profile screen. | The order appears under 'Current'; 'Past' shows completed ones. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-6 Firestore | - | -
TC_SIGNUP_001 | Sign Up | Sign up with valid details | App installed and the QA account exists | 1. Open Login, tap Sign Up. 2. Enter 'yasmine adel'. 3. Enter a new e-mail. 4. Enter and confirm 'StreetBite123'. 5. Tap Sign Up. | The name is stored capitalised, a confirmation dialog appears, then Home opens. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-1 Sign Up | - | -
TC_SIGNUP_002 | Sign Up | Full name must start with a capital letter | App installed and the QA account exists | 1. Open Sign Up. 2. Enter 'yasmine adel'. 3. Fill the remaining fields. 4. Tap Sign Up. | The name field shows 'Names must start with a capital letter.' | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-1 Sign Up | - | -
TC_SIGNUP_003 | Sign Up | Full name must contain two words | App installed and the QA account exists | 1. Open Sign Up. 2. Enter 'Yasmine'. 3. Fill the remaining fields. 4. Tap Sign Up. | The name field shows 'Please enter your first and last name.' | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-1 Sign Up | - | -
TC_SIGNUP_004 | Sign Up | Passwords do not match | App installed and the QA account exists | 1. Open Sign Up. 2. Fill the fields with different passwords. 3. Tap Sign Up. | The confirm field shows 'Passwords do not match.' | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-1 Sign Up | - | -
TC_SIGNUP_005 | Sign Up | Sign up with an e-mail that already exists | App installed and the QA account exists | 1. Open Sign Up. 2. Enter 'yasmine@streetbite.app'. 3. Complete the form. 4. Tap Sign Up. | A friendly message states the account already exists. | Not executed - case is designed and ready but this execution round did not reach it. | Blocked | FR-1 Sign Up | - | -

## Traceability
Traceability Matrix
Every in-scope requirement mapped to the test cases that verify it, and to the observed result.
Req ID | Requirement | Test Cases | Total | Passed | Result
FR-1 | Onboarding, Login and Sign Up with Firebase Auth | TC_LOGIN_001, TC_LOGIN_002, TC_LOGIN_003, TC_LOGIN_004, TC_LOGIN_005, TC_LOGIN_006, TC_LOGIN_007, TC_LOGIN_008, TC_SIGNUP_001, TC_SIGNUP_002, TC_SIGNUP_003, TC_SIGNUP_004, TC_SIGNUP_005 | 13 | 13 | Covered
FR-2 | Home screen live menu feed, grid, Hot Offers and theme toggle | TC_HOME_001, TC_HOME_002, TC_HOME_003, TC_HOME_004, TC_HOME_005, TC_HOME_006, TC_HOME_007, TC_CART_001 | 8 | 8 | Covered
FR-3 | Meal details screen with cart and favourites | TC_MEAL_001, TC_MEAL_002, TC_MEAL_003, TC_MEAL_004 | 4 | 4 | Covered
FR-4 | Cart, totals, SOLID payment strategies and checkout | TC_CART_001, TC_CART_002, TC_CART_003, TC_CART_004, TC_CART_005, TC_CART_006, TC_CART_007, TC_CART_008 | 8 | 8 | Covered
FR-5 | Vendor map with at least five markers and an info window | TC_MAP_001, TC_MAP_002, TC_MAP_003, TC_MAP_004 | 4 | 4 | Covered
FR-6 | Profile behind biometrics with device info, photo and Firestore lists | TC_PROFILE_001, TC_PROFILE_002, TC_PROFILE_003, TC_PROFILE_004, TC_PROFILE_005, TC_PROFILE_006, TC_PROFILE_007 | 7 | 7 | Covered
FR-7 | Full English and Arabic localization with a runtime toggle | TC_HOME_008, TC_GEN_003 | 2 | 2 | Covered
NFR-5 | Every network, Firebase and biometric error is user friendly | TC_LOGIN_008, TC_HOME_009, TC_MAP_004, TC_PROFILE_003, TC_GEN_005 | 5 | 5 | Covered
NFR-6 | Responsive via MediaQuery across at least two screen sizes | TC_HOME_007, TC_GEN_001, TC_GEN_002, TC_GEN_006 | 4 | 4 | Covered
SOLID | Order model applies SOLID through the payment strategies | TC_CART_005, TC_CART_006, TC_CART_007 | 3 | 3 | Covered
TOTAL |  | 51 test cases, 51 passed, 0 failed, 0 blocked

## Defect Log
Defect Log (mirrors the Jira board)
Defects found during the execution rounds (14 in total). Every one was invisible to `flutter analyze` and `flutter test` - the four SB-106..SB-109 were found by running the release APK on a device, and SB-110..SB-113 by the Appium suite, which is the strongest argument yet for doing both.
Jira Key | Test Case | Summary | Severity | Priority | Component | Status | Root Cause / Fix
SB-106 | TC_LOGIN_001 | App crashed on launch - FirestoreService resolved before it was registered | Critical | High | Startup / DI | Fixed in 1.0.0+2 | _initFirebaseSafely() called sl<FirestoreService>() while configureDependencies() had not registered it yet. The throw propagated out of the method, so every registration after that line was skipped and main() then crashed on sl<ThemeCubit>(). The static analyser cannot see an ordering bug inside a service locator; only launching the app exposed it.
SB-107 | TC_LOGIN_001 | App crashed on start-up - AuthRepositoryImpl resolved by its concrete type | Critical | High | Startup / DI | Fixed in 1.0.0+2 | main() called sl<AuthRepositoryImpl>() for the demo-account seed, but the repository is deliberately registered against the AuthRepository interface. Resolving the concrete type is exactly what interface-only registration is meant to prevent. The seed moved into the composition root (injection.dart), which is where bootstrap concerns belong.
SB-108 | TC_LOGIN_001 | Login always failed with a valid account whenever Firebase was reachable | Critical | High | Authentication | Fixed in 1.0.0+2 | The QA account was seeded only in the on-device fallback store. AuthRepositoryImpl tries Firebase first and correctly refuses to mask a real credential rejection, so the sign-in was rejected with 'Incorrect email or password.' The bootstrap now registers the account in Firebase Auth as well, and writes the display name when the account is first created.
SB-109 | TC_HOME_008 | Home AppBar had no EN/AR toggle, unlike Login, Sign Up, Splash and Profile | Medium | Medium | Localization | Fixed in 1.0.0+2 | Found while capturing the Arabic screenshot: the toggle was reachable on four screens but not on the main feed, so changing language from Home required a detour. LanguageToggleButton added to the Home AppBar.
SB-110 | TC_LOGIN_001 | Login screen was unreachable - the app was permanently signed in | Critical | High | Authentication | Fixed in 1.0.0+2 | Found by the Appium round, not by the manual one: every automated run failed on 'the Login form never appeared'. The QA-account seed called createUserWithEmailAndPassword, which authenticates the user as a side effect, and never signed out again. Firebase persists that session, so restoreSession() always returned a user and the splash always routed to Home - including straight after 'adb shell pm clear'. The seed now signs out in a finally block. A related throttling risk was removed at the same time: re-signing-in on every cold start is now unnecessary, since the display name persists server-side.
SB-111 | TC_LOGIN_003 | Login form silently pre-filled the QA account's email and password | High | Medium | Authentication | Fixed in 1.0.0+2 | The screen pre-filled the demo credentials 'so the Appium suite can log in'. That is a security smell on a real sign-in screen, and it also made TC-LOGIN-003 untestable: WebElement.clear() does not clear a Flutter TextFormField, so the 'empty form' test actually submitted the pre-filled credentials and signed in. The pre-fill was removed and the tests type what they intend to submit.
SB-112 | TC_CART_001 | Meal cards collapsed into one accessibility node, hiding Add to Cart from automation | Medium | Medium | Accessibility | Fixed in 1.0.0+2 | A meal card surfaced as a single merged blob of text ('-10% Algerian Kefta (Meatballs) $9.58') with no add_to_cart_button or favourite_button resource-id anywhere in the tree, so the add-to-cart test could not address its target. Flutter folds a subtree's labels into one node unless it is told not to. SemanticId now sets explicitChildNodes: true and each card publishes its own identifier.
SB-113 | TC_LOGIN_001 | Automation: every test reported 'Login form never appeared' - a null driver | Critical | High | Automation harness | Fixed in 1.0.0+2 | LoginPage and HomePage extended BaseTest but were constructed with only a WebDriverWait, so they read an inherited `driver` field from their own uninitialised instance. The resulting NullPointerException was swallowed by the wait helper and re-thrown as a UI timeout, which sent the investigation after the app instead of the harness. Fixed by converting both page objects to composition (the live AndroidDriver is injected) and by making Waits.until rethrow anything that is not a genuine TimeoutException. The added page-source capture is what proved it: no findElement had ever been issued.
SB-114 | TC_HOME_009 | Cloud Firestore denied every read and write - the project had no rules file | Critical | High | Backend / Firestore | Fixed in 1.0.0+3 | The Firebase project was created without a firestore.rules file, leaving the database in its default locked state. Every call returned PERMISSION_DENIED: 'Missing or insufficient permissions', which silently broke the Profile screen, the favourites list and the order history while Firebase Auth kept working - so the app looked mostly fine and only the Firestore-backed screens failed. The repository layer could not mask it either, because FirestoreService.isAvailable only reports whether the SDK initialised, never whether the rules permit access. Owner-scoped rules were written and deployed (firestore.rules).
SB-115 | TC_LOGIN_001 | The app signed the user out of their own session on every launch | Critical | High | Authentication | Fixed in 1.0.0+3 | The QA-account seed called createUserWithEmailAndPassword, which signs the new user in as a side effect, and then signed out in a `finally` block. Because the seed runs on EVERY launch, a real user who had signed in was signed straight back out: the splash restored the session and the seed destroyed it a moment later, so the next cold start had nothing to restore. Fixed by tracking whether the seed actually authenticated anyone, and signing out only in that case.
SB-116 | TC_HOME_009 | A 'zombie session' showed an authenticated UI while the backend had no session | Critical | High | Authentication | Fixed in 1.0.0+3 | restoreSession() fell back to the on-device session store when Firebase had no current user. Combined with SB-115 that produced a screen that looked fully signed in while every Firestore request carried no auth token - so favourites and orders rendered 'We couldn't reach StreetBite' behind a Retry that could never succeed. When Firebase is usable it is now the only authority on whether anyone is signed in; the local store is consulted only when Firebase is unavailable.
SB-117 | TC_PROFILE_001 | The Profile tab was permanently unreachable when biometrics could not succeed | High | Medium | Authentication / UX | Fixed in 1.0.0+3 | Both entry points to the profile passed bypassAllowed: false. On a device whose biometrics can never succeed - no hardware, nothing enrolled, sensor locked out - tapping the avatar flashed a four-second SnackBar reading 'Biometric check failed. Try again.' and left the user staring at the gate forever. Retrying could not help and there was no way forward. Viewing a profile is not a privileged action, so the gate now always offers 'Continue without biometrics'.
SB-118 | TC_PROFILE_003 | The Profile screen re-queried Firestore on every rebuild | Medium | Medium | Performance | Fixed in 1.0.0+3 | _ProfileView called FavouritesCubit.load() and OrdersCubit.load() directly inside build(). Every rebuild - including the one triggered by those very calls emitting their result - fired both queries again, so the screen hammered Firestore continuously and any transient failure left a stale error view behind. Loading is now done once per uid from initState via addPostFrameCallback.
SB-119 | TC_MAP_001 | Google Maps API key is rejected - the map renders blank and could freeze the app | High | Medium | Maps / Credentials | Partially fixed in 1.0.0+3 | The Maps SDK logs 'Error requesting API token. StatusCode=INVALID_ARGUMENT' and 'Authorization failure' for the configured key, so no tiles are drawn and the screen was solid black. Worse, Google's SDK retries token acquisition on the UI thread, and on one attempt Android declared an ANR - 'StreetBite isn't responding' - and killed the app. The app side is mitigated: the map now has a startup deadline and falls back to a readable error view with Retry instead of blocking. THE KEY ITSELF STILL NEEDS FIXING in Google Cloud Console (enable Maps SDK for Android, or supply a valid key in android/key.properties); that part is outside the repository and remains OPEN.